## Gantt Chart
Project Planner
[7 empty] | Period Highlight: |  |  |  |  | 6 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| Group 9 | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
| ACTIVITY: Flask Note Taking Web App | START | DURATION | START | DURATION | COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120
[7 empty] | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON
 | time axis 2021-08-19 to 2021-12-16
1 | Decide the project with team | 1 | 7 | 6 | 4 | 100% | bar: 2021-08-19
2 | Research possible resources | 3 | 20 | 6 | 8 | 100%
3 | Evaluate risks | 3 | 7 | 5 | 7 | 100%
4 | Tools and Libraries | 7 | 21 | 9 | 1 | 100%
5 | Research tools and libraries for project | 7 | 7 | 7 | 4 | 100%
6 | Study tools and libraries one-by-one | 7 | 14 | 7 | 3 | 100%
7 | Architect project pattern | 7 | 5 | 7 | 1 | 100%
8 | Construction | 7 | 10 | 7 | 27 | 100%
9 | Begin programming and design | 11 | 21 | 17 | 20 | 100%
10 | Refine programming and design | 21 | 14 | 31 | 3 | 100%
11 | Complete programming and design | 21 | 10 | 34 | 1 | 100%
12 | Final tests and corrections | 22 | 13 | 22 | 13 | 100%
13 | Progress | 30 | 5 | 36 | 1 | 100%
14 | Milestone 1 review | 33 | 2 | 36 | 1 | 100%
15 | Milestone 2 review | 34 | 4 | 37 | 1 | 100%
16 | Milestone 3 review | 34 | 4 | 34 | 2 | 100%
17 | Milestone 4 review | 34 | 4 | 34 | 2 | 100%
18 | Milestone 5 review | 34 | 4 | 34 | 2 | 100%
19 | Project Closeout | 38 | 1 | 37 | 2 | 100%
20 | Presentation and reports | 8 | 17 | 8 | 18 | 100%
21 | Speech preparation | 32 | 8 | 34 | 12 | 100%
22 | Submission and presentation | 48 | 10 | 45 | 10 | 100%